## 1. Overview
NomadFinance — Enterprise Project Tracker
Google Cloud AI Builder Cup 2026 — BFSI Track
Project Details
Project Name | NomadFinance
Domain | BFSI — Intelligent Risk, Fraud & Financial Experiences
Competition | Google Cloud AI Builder Cup 2026 (JAPAC)
Team Size | 3 (Devam, Aditya, Pranjal)
Kickoff Date | 2026-09-21
Prototype Deadline | 2026-10-18
Duration | 28 days
Grand Finale | 2026-12-04 (Singapore)
Prize Pool | USD 30,000
GitHub Org | google-ai-builder-cup
Repository | google-ai-builder-cup/NomadFinance
Deployment | Cloud Run (backend) + Firebase Hosting (frontend PWA)
Team Roles & Responsibilities
Owner | Role | Primary Responsibilities | Pillar Focus | Secondary | Tools
Devam | Full-Stack Engineer | Rotates across backend, frontend, data. Owns tasks in every pillar across every layer. | Cross-pillar contributor | Gemini pipelines, PWA polish, Firestore ops | Python, FastAPI, React, TypeScript, Firestore, Gemini
Aditya | Full-Stack Engineer | Rotates across backend, frontend, data. Owns tasks in every pillar across every layer. | Cross-pillar contributor | React PWA, Gemini pipelines, data ingestion | Python, FastAPI, React, TypeScript, Firestore, Gemini
Pranjal | Full-Stack Engineer | Rotates across backend, frontend, data. Owns tasks in every pillar across every layer. | Cross-pillar contributor | Firestore infra, React screens, Gemini pipelines | Python, FastAPI, React, TypeScript, Firestore, Gemini
Sheet Index
Sheet | Purpose
1. Overview | This sheet — project summary, team, key dates
2. Master Tracker | All 100+ tasks across all phases with IDs, owners, dates, dependencies, status
3. Phase 0 - Setup | Detailed Day 1 pre-build setup checklist (Sep 21)
4. Sprint Timeline | Week-by-week Gantt-style timeline view
5. Workload Balance | Task distribution + hour estimates per teammate
6. Git Standards | Branching model, commit conventions, PR process, code review checklist
7. Coding Standards | Python + TypeScript conventions, linting, testing
8. Definition of Done | Acceptance criteria per task type
9. Risk Register | Known risks, likelihood, impact, mitigation
10. Daily Standup | Standup log template — daily updates
11. Dependencies | Cross-team dependency matrix
12. AI Assistant Policy | Rules for using Claude/AI without polluting Git history
13. Submission Checklist | Final Oct 18 submission requirements verification
14. Parallel Workflow | Day-by-day parallel execution plan + critical path + handoff matrix
Pillar & Feature Coverage Verification
Pillar / Feature | Task Count | Task IDs (Sample)
Pillar 1: Remittance X-Ray | 10 | P1-015, P1-016, P1-019, P2-014-020, P2-022, P3-022 |  |  | COMPLETE
Pillar 2: Contract Shield | 16 | P1-006, P1-017, P1-018, P2-001-013, P2-021, P2-023, P3-020, P3-023, P3-024 |  |  | COMPLETE
Pillar 3: Exploitation Radar | 12 | P2-021, P3-001-009, P3-022, P3-025 |  |  | COMPLETE
Pillar 4: Financial Identity | 11 | P2-017, P3-010-018, P3-021, P3-024 |  |  | COMPLETE
Cross-Pillar Data Flow | 5 | P2-017 (P1→P4), P2-021 (P2→P3), P3-022 (P3→P1), P3-023 (P3→P2), P3-024 (P2→P4) |  |  | COMPLETE
Authentication (Firebase Auth) | 3 | P1-005, P1-009, P1-022 |  |  | COMPLETE
Onboarding + Profile | 2 | P1-022, P1-023 |  |  | COMPLETE
i18n (6 languages) | 1 | P1-011 |  |  | COMPLETE
PWA + Offline | 2 | P1-012, P1-024 |  |  | COMPLETE
Design Assets + Branding | 1 | P1-024 |  |  | COMPLETE
Analytics | 1 | P1-025 |  |  | COMPLETE
Middleware (CORS, Rate Limit, Logging) | 3 | P1-026, P1-027, P1-028 |  |  | COMPLETE
Gemini Integration (3 models) | 10+ | P1-004, P1-029, P2-001-006, P3-001-013 |  |  | COMPLETE
CI/CD | 1 | P1-020 |  |  | COMPLETE
Cron Jobs | 3 | P1-019, P3-004, P3-013 |  |  | COMPLETE
Testing (E2E, cross-browser, security) | 4 | P2-008, P4-001, P4-002, P4-004 |  |  | COMPLETE
Documentation (README, API, Data Model) | 4 | P4-011, P4-017, P4-020, docs/ throughout |  |  | COMPLETE
Demo Video (3-4 min) | 3 | P4-005, P4-006, P4-007, P4-019 (rehearsal) |  |  | COMPLETE
Pitch Deck | 4 | P4-008, P4-009, P4-010, P4-018 (bios) |  |  | COMPLETE
Live Deployment | 3 | P1-003, P1-008, P4-013 |  |  | COMPLETE
Submission Portal | 2 | P4-012, P4-015 |  |  | COMPLETE
Demo Data (contracts + users) | 3 | P3-005, P3-020, P3-021 |  |  | COMPLETE

## 2. Master Tracker
Master Task Tracker — All Phases
Filter by status/owner/phase using column filters. Update Status as work progresses.
Task ID | Phase | Category | Task Title | Description | Owner | Priority | Est. Hours | Start Date | End Date | Dependencies | Status | Notes
NF-P0-001 | Phase 0 | Setup | Create GitHub Org & Repo | Create google-ai-builder-cup org, invite all 3 as owners, initialize public repo with README/LICENSE/.gitignore | Aditya | P0 | 1 | 2026-09-21 | 2026-09-21 | - | Done | COMPLETED
NF-P0-002 | Phase 0 | Setup | Make Repo Public | Change repo visibility from Private to Public in Settings > Danger Zone | Aditya | P0 | 0.25 | 2026-09-21 | 2026-09-21 | NF-P0-001 | Done | Judges cannot access private repos
NF-P0-003 | Phase 0 | Setup | Configure Local Git Identity | Each teammate runs git config user.name and user.email with GitHub-verified email | All | P0 | 0.25 | 2026-09-21 | 2026-09-21 | NF-P0-001 | Done | Contributions won't count without correct email
NF-P0-004 | Phase 0 | Setup | Create Google Cloud Project | Create GCP project 'nomadfinance-prod', enable billing (no charges expected), enable required APIs | Devam | P0 | 1 | 2026-09-21 | 2026-09-21 | - | Not Started | APIs: Firestore, Cloud Run, Cloud Build, Secret Manager, Cloud Scheduler, AI Platform
NF-P0-005 | Phase 0 | Setup | Create Firebase Project | Link Firebase to GCP project. Enable Auth (Google + Phone), Firestore, Storage, Hosting, App Check, FCM | Pranjal | P0 | 1 | 2026-09-21 | 2026-09-21 | NF-P0-004 | Not Started | Same project = same billing
NF-P0-006 | Phase 0 | Setup | Get Gemini API Key | Generate from AI Studio, store in Secret Manager (secret name: gemini-api-key) | Devam | P0 | 0.5 | 2026-09-21 | 2026-09-21 | NF-P0-004 | Not Started | Never commit to git
NF-P0-007 | Phase 0 | Setup | Invite Team to Cloud Project | Add Pranjal + Aditya as Owners on GCP project via IAM | Devam | P0 | 0.25 | 2026-09-21 | 2026-09-21 | NF-P0-004 | Not Started | -
NF-P0-008 | Phase 0 | Setup | Initialize Local Dev Environments | Everyone installs Python 3.11, Node 20+, Docker Desktop, Firebase CLI, gcloud CLI | All | P0 | 2 | 2026-09-21 | 2026-09-21 | - | Not Started | Run firebase login and gcloud auth login
NF-P0-009 | Phase 0 | Setup | Create Initial Folder Structure | Push backend/, frontend/, data-scripts/, docs/ folders with README stubs. Sequential commits. | All | P0 | 1 | 2026-09-21 | 2026-09-21 | NF-P0-003 | Not Started | One folder per person, rotating
NF-P0-010 | Phase 0 | Setup | Set Up Communication Channels | WhatsApp group, Google Meet link for daily standup, shared Google Drive for pitch assets | Aditya | P0 | 0.5 | 2026-09-21 | 2026-09-21 | - | Not Started | Daily standup: 9:30 PM IST
NF-P0-011 | Phase 0 | Setup | Kickoff Meeting | Team call to review design doc, confirm task rotation, walk through timeline, agree on standup time | All | P0 | 1 | 2026-09-21 | 2026-09-21 | NF-P0-010 | Not Started | 1 hour
NF-P0-012 | Phase 0 | Setup | Create GitHub Project Board | Set up Projects board in GitHub org with columns: Backlog, In Progress, Review, Done. Import all tasks. | Pranjal | P0 | 1 | 2026-09-21 | 2026-09-21 | NF-P0-001 | Not Started | -
NF-P0-013 | Phase 0 | Setup | Add .gitignore + .claude Exclusions | Add comprehensive .gitignore including .claude/, .env, __pycache__/, node_modules/, dist/ | Devam | P0 | 0.5 | 2026-09-21 | 2026-09-21 | NF-P0-002 | Not Started | See sheet 12 for AI Assistant Policy
NF-P0-014 | Phase 0 | Setup | Pin Repo on All Profiles | Each teammate pins google-ai-builder-cup/NomadFinance on their GitHub profile + makes org visibility public | All | P0 | 0.25 | 2026-09-21 | 2026-09-21 | NF-P0-002 | Not Started | -
NF-P1-001 | Week 1 | Backend | Bootstrap FastAPI Project | Initialize FastAPI app with /health endpoint, Pydantic v2, Uvicorn, Gunicorn, requirements.txt | Devam | P0 | 3 | 2026-09-22 | 2026-09-22 | NF-P0-009 | Not Started | -
NF-P1-002 | Week 1 | Backend | Dockerize Backend | Multi-stage Dockerfile with python:3.11-slim base. Build locally, verify /health responds. | Devam | P0 | 3 | 2026-09-22 | 2026-09-23 | NF-P1-001 | Not Started | -
NF-P1-003 | Week 1 | DevOps | Deploy Hello World to Cloud Run | Manual first deploy via gcloud CLI. Verify public URL responds. Document steps in README. | Pranjal | P0 | 3 | 2026-09-23 | 2026-09-23 | NF-P1-002,NF-P0-004 | Not Started | Verify pipeline works BEFORE writing real code
NF-P1-004 | Week 1 | Backend | Gemini Client Wrapper | Reusable class handling all Gemini calls (model routing, structured output, retries, error handling) | Devam | P0 | 6 | 2026-09-24 | 2026-09-25 | NF-P1-003,NF-P0-006 | Not Started | Use google-genai SDK + tenacity for retries
NF-P1-005 | Week 1 | Backend | Firebase Admin Integration | Setup firebase-admin SDK, verify Firestore read/write, implement Auth token verification middleware | Aditya | P0 | 4 | 2026-09-25 | 2026-09-26 | NF-P1-003,NF-P0-005 | Not Started | Backend rotation for Aditya
NF-P1-006 | Week 1 | Backend | Basic Document Extraction Endpoint | POST /documents/extract: accept file upload, send to Gemini Vision, return structured text. E2E test. | Devam | P0 | 5 | 2026-09-26 | 2026-09-27 | NF-P1-004,NF-P1-005 | Not Started | Foundation for Contract Shield
NF-P1-007 | Week 1 | Frontend | Bootstrap React + Vite Project | Initialize React 18 + Vite + TypeScript. Install Tailwind, shadcn/ui, React Router, TanStack Query | Aditya | P0 | 3 | 2026-09-22 | 2026-09-22 | NF-P0-009 | Not Started | -
NF-P1-008 | Week 1 | Frontend | Deploy Skeleton to Firebase Hosting | Configure firebase.json, run firebase deploy. Verify public URL loads. Document in README. | Aditya | P0 | 2 | 2026-09-22 | 2026-09-23 | NF-P1-007,NF-P0-005 | Not Started | -
NF-P1-009 | Week 1 | Frontend | Firebase Auth Integration | Implement Google sign-in + Phone OTP flows. Auth context provider. Protected route wrapper. | Devam | P0 | 6 | 2026-09-23 | 2026-09-24 | NF-P1-008 | Not Started | Frontend rotation for Devam
NF-P1-010 | Week 1 | Frontend | App Shell + Navigation | Layout, header, footer, dashboard skeleton with 4 pillar cards. Mobile-first responsive. | Pranjal | P0 | 4 | 2026-09-24 | 2026-09-25 | NF-P1-009 | Not Started | Frontend rotation for Pranjal
NF-P1-011 | Week 1 | Frontend | i18n Setup (6 languages) | react-i18next configured. JSON files for EN, HI, TL, ID, NE, BN. Language selector in header. | Aditya | P0 | 4 | 2026-09-25 | 2026-09-26 | NF-P1-010 | Not Started | Static UI strings only in Week 1
NF-P1-012 | Week 1 | Frontend | PWA Setup | vite-plugin-pwa configured. Manifest, service worker, install prompt. Verify installable on mobile. | Aditya | P1 | 3 | 2026-09-26 | 2026-09-27 | NF-P1-011 | Not Started | -
NF-P1-013 | Week 1 | Data | Design Firestore Schema | Document collection structures per design doc. Create schema markdown in docs/data-model.md. | Pranjal | P0 | 3 | 2026-09-22 | 2026-09-22 | NF-P0-009 | Not Started | -
NF-P1-014 | Week 1 | Data | Firestore Security Rules | Write firestore.rules for user data isolation. Test with Emulator. Deploy via firebase deploy. | Devam | P0 | 3 | 2026-09-22 | 2026-09-23 | NF-P1-013 | Not Started | Data rotation for Devam
NF-P1-015 | Week 1 | Data | Download & Parse World Bank RPW Data | Download RPW Excel. Write Python script (pandas + openpyxl) to parse 6 corridors. Sample validation. | Pranjal | P0 | 6 | 2026-09-23 | 2026-09-24 | - | Not Started | 6 corridors, ~48 provider records
NF-P1-016 | Week 1 | Data | Load Corridor Data into Firestore | data-scripts/load_corridors.py: authenticated bulk write to Firestore corridors/ collection | Aditya | P0 | 3 | 2026-09-24 | 2026-09-25 | NF-P1-015,NF-P1-014 | Not Started | Data rotation for Aditya
NF-P1-017 | Week 1 | Data | Curate ILO NATLEX Labor Laws (Split 3-way) | Manual curation for 6 host countries. Devam=SG+AE, Aditya=KR+MY, Pranjal=JP+HK. 15 categories each. | All | P0 | 18 | 2026-09-22 | 2026-09-26 | - | Not Started | REVISED: 6 hrs each × 2 countries. 15 categories × ~24 min each is realistic; 12h was too tight for legal research.
NF-P1-018 | Week 1 | Data | Load Labor Laws into Firestore | data-scripts/load_labor_laws.py: bulk write with version metadata (_meta document per country) | Pranjal | P0 | 3 | 2026-09-26 | 2026-09-27 | NF-P1-017 | Not Started | -
NF-P1-019 | Week 1 | DevOps | Cloud Scheduler + FX Refresh Cron | Endpoint POST /internal/refresh-rates. Cloud Scheduler config. IAM auth for cron. Verify hourly runs. | Devam | P1 | 4 | 2026-09-25 | 2026-09-27 | NF-P1-003 | Not Started | DevOps rotation for Devam
NF-P1-020 | Week 1 | DevOps | GitHub Actions CI/CD | Two workflows: backend (Docker build + Cloud Run deploy), frontend (Vite build + Firebase deploy) | Pranjal | P0 | 5 | 2026-09-24 | 2026-09-27 | NF-P1-003,NF-P1-008 | Not Started | Use OIDC federation, not JSON keys
NF-P1-021 | Week 1 | Frontend | Landing Page + Emotional Hook | Public landing at /. 'Meet Priya' story, 4 pillar previews, sign-in CTA. Mobile-first. | Aditya | P0 | 4 | 2026-09-26 | 2026-09-27 | NF-P1-011 | Not Started | First thing judges see
NF-P1-022 | Week 1 | Full-Stack | User Onboarding Flow | Post-signin: capture home_country, host_country, job_type, preferred_language. Save to Firestore. | Devam | P0 | 5 | 2026-09-25 | 2026-09-27 | NF-P1-005,NF-P1-009 | Not Started | Drives personalization across all pillars
NF-P1-023 | Week 1 | Frontend | User Profile / Settings Page | View + edit profile. Change language, host country, notification preferences. Delete account. | Pranjal | P1 | 3 | 2026-09-26 | 2026-09-27 | NF-P1-022 | Not Started | Frontend rotation for Pranjal
NF-P1-024 | Week 1 | Frontend | Design Assets — Logo + Colors + Favicons | Logo (2 variants), color palette, favicon suite (16-512px), PWA icons, splash screens. | Aditya | P1 | 3 | 2026-09-24 | 2026-09-25 | - | Not Started | Also feeds pitch deck branding
NF-P1-025 | Week 1 | Data | Firebase Analytics Setup | Enable Analytics SDK. Define custom events (pillar_used, contract_analyzed). User properties. | Pranjal | P1 | 2 | 2026-09-26 | 2026-09-27 | NF-P1-007 | Not Started | Screenshots for pitch metrics
NF-P1-026 | Week 1 | Frontend | Error Boundaries + Toast Notifications | React ErrorBoundary at app root. Global toast system for user-facing errors. Retry actions. | Devam | P1 | 2 | 2026-09-27 | 2026-09-27 | NF-P1-010 | Not Started | Frontend rotation for Devam
NF-P1-027 | Week 1 | Backend | CORS + Rate Limiting Middleware | FastAPI CORS for frontend origin. slowapi rate limiting (60 rpm default). Bypass for internal cron. | Devam | P0 | 2 | 2026-09-24 | 2026-09-25 | NF-P1-001 | Not Started | -
NF-P1-028 | Week 1 | Backend | Structured Logging Middleware | Request ID injection, user ID (hashed), latency logging. JSON output to Cloud Logging. | Pranjal | P1 | 2 | 2026-09-25 | 2026-09-26 | NF-P1-001 | Not Started | Backend rotation for Pranjal
NF-P1-029 | Week 1 | Backend | Gemini Prompt Library | backend/prompts/ folder with all system prompts + user templates. Versioned per pipeline step. | Devam | P0 | 3 | 2026-09-25 | 2026-09-27 | NF-P1-004 | Not Started | Central place for all Gemini prompts — easier to iterate
NF-P2-001 | Week 2 | Backend | Contract Shield: Text Extraction Step | Pipeline step 1: Gemini 1.5 Flash Vision. Extract raw text + preserve structure. Structured output. | Devam | P0 | 4 | 2026-09-28 | 2026-09-28 | NF-P1-006 | Not Started | -
NF-P2-002 | Week 2 | Backend | Contract Shield: Language + Country Detection | Pipeline step 2: Gemini 1.5 Flash. Detect source language, host country, contract type. | Pranjal | P0 | 3 | 2026-09-28 | 2026-09-29 | NF-P2-001 | Not Started | Backend rotation for Pranjal
NF-P2-003 | Week 2 | Backend | Contract Shield: Labor Law RAG Retrieval | Pipeline step 3: Firestore query by detected country. Return structured law rules. | Aditya | P0 | 3 | 2026-09-29 | 2026-09-29 | NF-P2-002,NF-P1-018 | Not Started | Backend rotation for Aditya
NF-P2-004 | Week 2 | Backend | Contract Shield: Clause Comparison | Pipeline step 4: Gemini 2.5 Flash. Clause-by-clause comparison. Risk scoring per clause. JSON output. | Devam | P0 | 6 | 2026-09-29 | 2026-09-30 | NF-P2-003 | Not Started | Core reasoning step
NF-P2-005 | Week 2 | Backend | Contract Shield: Translation Step | Pipeline step 5: Gemini Flash-Lite. Translate full report to user language. | Aditya | P0 | 3 | 2026-09-30 | 2026-10-01 | NF-P2-004 | Not Started | -
NF-P2-006 | Week 2 | Backend | Contract Shield: Complaint Generator | Pipeline step 6: If violations found, generate formal complaint template using Gemini 2.5 Flash. | Pranjal | P0 | 4 | 2026-10-01 | 2026-10-02 | NF-P2-005 | Not Started | Backend rotation for Pranjal
NF-P2-007 | Week 2 | Backend | Contract Shield: Response Caching | Cache by contract-hash + language + law-version. Serve cached on repeat. | Devam | P1 | 3 | 2026-10-02 | 2026-10-03 | NF-P2-006 | Not Started | -
NF-P2-008 | Week 2 | QA | Contract Shield: E2E Testing | Test with 5 real sample contracts (SG, AE, KR, MY, JP). Fix edge cases. Latency profiling. | All | P0 | 4 | 2026-10-03 | 2026-10-04 | NF-P2-007 | Not Started | Team testing — 1 sample per person + shared review
NF-P2-009 | Week 2 | Frontend | Contract Shield: Upload UI | react-dropzone + camera capture. File preview. Language + country selection form. | Aditya | P0 | 4 | 2026-09-28 | 2026-09-29 | NF-P1-012 | Not Started | -
NF-P2-010 | Week 2 | Frontend | Contract Shield: Processing Animation | Multi-step processing indicator showing pipeline progress. Skeleton loader. | Devam | P0 | 3 | 2026-09-29 | 2026-09-30 | NF-P2-009 | Not Started | Frontend rotation for Devam
NF-P2-011 | Week 2 | Frontend | Contract Shield: Report Card UI | Clause-by-clause view with 🟢🟡🔴 flags. Side-by-side contract vs law. Risk score header. | Aditya | P0 | 8 | 2026-09-30 | 2026-10-02 | NF-P2-010 | Not Started | Biggest UI task of Week 2
NF-P2-012 | Week 2 | Frontend | Contract Shield: Language Switcher on Report | Toggle report language without re-uploading. Fetch translation from cache. | Pranjal | P0 | 3 | 2026-10-02 | 2026-10-03 | NF-P2-011 | Not Started | Frontend rotation for Pranjal
NF-P2-013 | Week 2 | Frontend | Contract Shield: Complaint Letter Download | Preview complaint letter, download as PDF, copy to clipboard actions. | Aditya | P0 | 3 | 2026-10-03 | 2026-10-04 | NF-P2-012 | Not Started | -
NF-P2-014 | Week 2 | Backend | Remittance: Comparison Engine | POST /remittance/compare: fetch providers + live rate, calculate true cost, rank, return JSON. | Pranjal | P0 | 5 | 2026-09-28 | 2026-09-30 | NF-P1-016,NF-P1-019 | Not Started | -
NF-P2-015 | Week 2 | Backend | Remittance: Historical Trends Endpoint | GET /remittance/trends: return historical rate data for trend charts. | Devam | P1 | 3 | 2026-09-30 | 2026-10-01 | NF-P2-014 | Not Started | Backend rotation for Devam
NF-P2-016 | Week 2 | Backend | Remittance: Gemini Recommendation | Gemini Flash-Lite generates personalized recommendation from comparison data. | Pranjal | P0 | 3 | 2026-10-01 | 2026-10-02 | NF-P2-014,NF-P1-004 | Not Started | -
NF-P2-017 | Week 2 | Backend | Remittance: Transfer Logging | POST /remittance/log: user logs a transfer. Feeds Financial Identity. | Aditya | P1 | 3 | 2026-10-02 | 2026-10-03 | NF-P2-016 | Not Started | Backend rotation for Aditya
NF-P2-018 | Week 2 | Frontend | Remittance: Corridor + Amount Selector | Form UI with corridor dropdown, amount input, currency indicator. | Devam | P0 | 3 | 2026-10-04 | 2026-10-04 | NF-P2-013 | Not Started | Frontend rotation for Devam
NF-P2-019 | Week 2 | Frontend | Remittance: Comparison Table | Provider comparison with sortable columns, savings highlight, recipient-receives display. | Aditya | P0 | 4 | 2026-10-04 | 2026-10-05 | NF-P2-018,NF-P2-014 | Not Started | -
NF-P2-020 | Week 2 | Frontend | Remittance: Trend Chart | Recharts historical trend chart. Best day to send indicator. | Pranjal | P1 | 3 | 2026-10-05 | 2026-10-05 | NF-P2-019,NF-P2-015 | Not Started | Frontend rotation for Pranjal
NF-P2-021 | Week 2 | Backend | Cross-Pillar: Contract Flags → Radar Signal | When Contract Shield flags an employer/agency, auto-create anonymized radar_reports entry. | Pranjal | P0 | 4 | 2026-10-03 | 2026-10-04 | NF-P2-004 | Not Started | Ecosystem story — pillars feed each other
NF-P2-022 | Week 2 | Backend | Remittance: Historical Savings Calculator | GET /remittance/savings: given corridor + amount + months, compute what user would have saved vs mid-market over the period. Powers 'you would have saved $X' hero moment in demo. | Devam | P0 | 3 | 2026-10-01 | 2026-10-02 | NF-P2-015 | Not Started | NEW: Demo hero moment from design doc §2.1 that was missing from tracker.
NF-P2-023 | Week 2 | Frontend | Contract Shield: Report Card Interactions & Polish | Pair task with P2-011: language toggle wiring, clause expand/collapse, risk score tooltip, sticky side-by-side columns, mobile responsive tuning. | Pranjal | P0 | 4 | 2026-10-02 | 2026-10-03 | NF-P2-011 | Not Started | NEW: Split from P2-011 to de-risk 8h estimate on complex UI. Pair with Aditya.
NF-P3-001 | Week 3 | Backend | Radar: Report Submission Endpoint | POST /radar/report: accept report, validate via Gemini, extract entity, categorize. | Pranjal | P0 | 5 | 2026-10-05 | 2026-10-06 | NF-P1-004 | Not Started | -
NF-P3-002 | Week 3 | Backend | Radar: Embedding + Clustering | Generate embeddings via text-embedding-004. Firestore Vector Search for similarity. | Aditya | P0 | 5 | 2026-10-06 | 2026-10-07 | NF-P3-001 | Not Started | Backend rotation for Aditya
NF-P3-003 | Week 3 | Backend | Radar: Entity Risk Aggregation | Update radar_entities/ risk profile when new reports come in. Recompute rating. | Pranjal | P0 | 4 | 2026-10-07 | 2026-10-08 | NF-P3-002 | Not Started | -
NF-P3-004 | Week 3 | Backend | Radar: Alert Cron Job | Cloud Scheduler every 6h: detect surges, generate alerts, push via FCM. | Devam | P1 | 4 | 2026-10-08 | 2026-10-09 | NF-P3-003 | Not Started | Backend rotation for Devam
NF-P3-005 | Week 3 | Data | Radar: Seed Data for Demo | Load 15-20 synthetic reports across corridors so heatmap looks populated in demo. | Pranjal | P0 | 3 | 2026-10-09 | 2026-10-10 | NF-P3-003 | Not Started | CRITICAL for demo
NF-P3-006 | Week 3 | Frontend | Radar: Report Submission Form | Multi-step form (entity type, name, corridor, violation, description). Image upload optional. | Devam | P0 | 5 | 2026-10-05 | 2026-10-06 | NF-P2-020 | Not Started | Frontend rotation for Devam
NF-P3-007 | Week 3 | Frontend | Radar: Heatmap Map View | react-leaflet + OpenStreetMap. Corridor-level heat overlay. Marker clustering. | Aditya | P0 | 8 | 2026-10-06 | 2026-10-08 | NF-P3-006 | Not Started | Complex, allocate full 2 days
NF-P3-008 | Week 3 | Frontend | Radar: Entity Profile Page | Aggregated report list per entity. Community rating. Report count. Risk badge. | Pranjal | P0 | 4 | 2026-10-08 | 2026-10-09 | NF-P3-007 | Not Started | Frontend rotation for Pranjal
NF-P3-009 | Week 3 | Frontend | Radar: Alert Feed | Notification list with FCM integration. Read/unread state. Deep links. | Aditya | P1 | 3 | 2026-10-09 | 2026-10-10 | NF-P3-008,NF-P3-004 | Not Started | -
NF-P3-010 | Week 3 | Backend | FIB: Activity Logging Endpoints | POST /fib/income, /fib/bill, /fib/savings. Structured Pydantic models. Firestore writes. | Aditya | P0 | 4 | 2026-10-05 | 2026-10-06 | NF-P2-008 | Not Started | Backend rotation for Aditya
NF-P3-011 | Week 3 | Backend | FIB: Bill OCR Extraction | Gemini Vision extracts structured bill data (amount, vendor, date, category). | Devam | P0 | 4 | 2026-10-06 | 2026-10-07 | NF-P3-010 | Not Started | -
NF-P3-012 | Week 3 | Backend | FIB: Transaction Categorization | Gemini Flash-Lite classifies each entry into categories. Batch process. | Pranjal | P1 | 3 | 2026-10-07 | 2026-10-07 | NF-P3-011 | Not Started | Backend rotation for Pranjal
NF-P3-013 | Week 3 | Backend | FIB: Weekly Profile Recompute | Cloud Scheduler weekly job. Compute metrics (income stability, savings rate, etc). Gemini synthesizes narrative. | Devam | P0 | 5 | 2026-10-07 | 2026-10-09 | NF-P3-012 | Not Started | -
NF-P3-014 | Week 3 | Backend | FIB: PDF Report Export | weasyprint generates portable Financial Identity PDF. Cloud Storage. Signed download URL. | Aditya | P0 | 4 | 2026-10-09 | 2026-10-10 | NF-P3-013 | Not Started | -
NF-P3-015 | Week 3 | Data | FIB: Demo User with History | Seed a demo user with 6 months of synthetic activity for pitch demo. | Pranjal | P0 | 3 | 2026-10-10 | 2026-10-11 | NF-P3-014 | Not Started | CRITICAL for demo
NF-P3-016 | Week 3 | Frontend | FIB: Log Activity UI | Tabs for Income / Transfer / Bill / Savings. Quick entry forms. Camera for bill upload. | Devam | P0 | 5 | 2026-10-10 | 2026-10-11 | NF-P3-009 | Not Started | Frontend rotation for Devam
NF-P3-017 | Week 3 | Frontend | FIB: Financial Timeline Dashboard | Chart of income/expenses over time. Savings rate meter. Category breakdown. | Pranjal | P0 | 5 | 2026-10-11 | 2026-10-11 | NF-P3-016 | Not Started | REASSIGNED: Aditya → Pranjal to rebalance Week 3 (Aditya was carrying 37h). Frontend rotation for Pranjal.
NF-P3-018 | Week 3 | Frontend | FIB: Portable Report Export UI | Trigger PDF generation. Preview modal. Download + share buttons. | Pranjal | P0 | 3 | 2026-10-11 | 2026-10-11 | NF-P3-017,NF-P3-014 | Not Started | Frontend rotation for Pranjal
NF-P3-019 | Week 3 | Frontend | Home Dashboard Tying All Pillars | Signed-in home shows: recent contracts, remittance shortcut, radar alerts, FIB progress. Widget grid. | Aditya | P0 | 5 | 2026-10-10 | 2026-10-11 | NF-P3-017 | Not Started | Anchors the ecosystem story
NF-P3-020 | Week 3 | Data | Sample Contracts for Demo (6 countries) | Curate/create 6 realistic sample contracts, one per host country. Store in Cloud Storage. | Pranjal | P0 | 4 | 2026-10-08 | 2026-10-10 | NF-P2-008 | Not Started | CRITICAL — no contracts = no demo
NF-P3-021 | Week 3 | Data | Demo User Accounts (Pre-seeded) | Create 3 demo users: Priya (SG domestic), Rajesh (UAE construction), Miguel (JP care). Full activity data. | Devam | P0 | 3 | 2026-10-10 | 2026-10-11 | NF-P3-015 | Not Started | For demo video — judges see rich, real-feeling data
NF-P3-022 | Week 3 | Frontend | Cross-Pillar: Radar Warnings in Remittance UI | Show 'community flagged' warning badge next to any provider with active radar reports. | Aditya | P0 | 3 | 2026-10-08 | 2026-10-09 | NF-P2-019,NF-P3-003 | Not Started | Cross-pillar data flow story
NF-P3-023 | Week 3 | Frontend | Cross-Pillar: Radar Warnings on Contract Shield | In Contract Report Card, check detected employer/agency name against radar_entities/. If flagged, show ⚠ 'Community flagged — N reports' badge with link to entity profile. | Pranjal | P0 | 3 | 2026-10-09 | 2026-10-10 | NF-P3-003,NF-P2-011 | Not Started | NEW: Cross-pillar flow #4 (P3 → P2) from design doc §5.6 — was missing.
NF-P3-024 | Week 3 | Backend | Cross-Pillar: Contract Employment → FIB Income Source | When Contract Shield analyzes an employment contract, extract stated salary + employer and log as 'verified employment' income source in FIB. Feeds Financial Identity narrative. | Devam | P1 | 3 | 2026-10-08 | 2026-10-09 | NF-P2-004,NF-P3-010 | Not Started | NEW: Cross-pillar flow #5 (P2 → P4) from design doc §5.6 — was missing.
NF-P3-025 | Week 3 | Backend | Radar: Firebase App Check Enforcement | Wire App Check enforcement to POST /radar/report. Verify reCAPTCHA v3 token, reject if score < 0.5. Prevents demo-day trolling of the crowdsourced submission form. | Pranjal | P1 | 2 | 2026-10-06 | 2026-10-07 | NF-P3-001 | Not Started | NEW: Anti-abuse from design doc §4.1 — App Check was enabled but not wired to endpoint.
NF-P4-001 | Week 4 | QA | E2E Testing All Pillars | Mobile + desktop. Slow network. Edge cases per pillar. Log bugs. Fix P0 bugs immediately. | All | P0 | 8 | 2026-10-12 | 2026-10-13 | NF-P3-018 | Not Started | -
NF-P4-002 | Week 4 | QA | Cross-browser Testing | Chrome Android + Safari iOS + desktop Chrome/Firefox. Fix rendering issues. | Aditya | P0 | 4 | 2026-10-12 | 2026-10-13 | NF-P4-001 | Not Started | -
NF-P4-003 | Week 4 | QA | Performance Profiling | Lighthouse scores. Firestore query optimization. Gemini call latency review. | Devam | P1 | 4 | 2026-10-13 | 2026-10-14 | NF-P4-001 | Not Started | -
NF-P4-004 | Week 4 | QA | Security Audit | Firestore rules review. Auth bypass tests. Secret leak scan. Rate limiting verification. | Pranjal | P0 | 4 | 2026-10-13 | 2026-10-14 | NF-P4-001 | Not Started | -
NF-P4-005 | Week 4 | Demo | Prepare Demo Script | Write 3-4 min narration. Practice with real contracts + demo users. Timing check. | All | P0 | 4 | 2026-10-14 | 2026-10-14 | NF-P4-001 | Not Started | Team writes together
NF-P4-006 | Week 4 | Demo | Record Demo Video | Screen recording via OBS. Voice-over. Subtitles. Multiple takes if needed. Export to MP4. | Aditya | P0 | 6 | 2026-10-14 | 2026-10-15 | NF-P4-005 | Not Started | 3-4 min max
NF-P4-007 | Week 4 | Demo | Upload Video to YouTube | Unlisted YouTube upload. Verify link works. Backup on Google Drive. | Devam | P0 | 1 | 2026-10-15 | 2026-10-15 | NF-P4-006 | Not Started | -
NF-P4-008 | Week 4 | Submission | Draft Pitch Deck | Follow prescribed template. Slides: Problem, Solution, Demo, Tech, Impact, Roadmap, Team. | All | P0 | 8 | 2026-10-14 | 2026-10-16 | NF-P4-001 | Not Started | Team writes together
NF-P4-009 | Week 4 | Submission | Design Pitch Deck Visuals | Charts, screenshots, architecture diagrams, team photos. Consistent branding. | Aditya | P0 | 5 | 2026-10-15 | 2026-10-16 | NF-P4-008 | Not Started | -
NF-P4-010 | Week 4 | Submission | Export Deck to PDF | Convert final deck to PDF per submission requirements. | Pranjal | P0 | 0.5 | 2026-10-16 | 2026-10-16 | NF-P4-009 | Not Started | -
NF-P4-011 | Week 4 | Submission | Update Root README | Judge-friendly setup, architecture diagram, stack summary, Firebase/Firestore/CloudRun/Gemini usage. | Devam | P0 | 3 | 2026-10-15 | 2026-10-16 | NF-P4-001 | Not Started | -
NF-P4-012 | Week 4 | Submission | Write Submission Brief | 3-4 paragraph description for submission form mentioning Firebase, Firestore, Cloud Run, Gemini. | Pranjal | P0 | 1 | 2026-10-16 | 2026-10-16 | NF-P4-011 | Not Started | -
NF-P4-013 | Week 4 | Submission | Final Deployment Verification | Fresh browser session, incognito, no state. Test all 4 pillars end-to-end. | Aditya | P0 | 3 | 2026-10-16 | 2026-10-17 | NF-P4-004 | Not Started | -
NF-P4-014 | Week 4 | Submission | Freeze Main Branch | No more commits. Tag release v1.0-submission. Notify team. | Devam | P0 | 0.5 | 2026-10-17 | 2026-10-17 | NF-P4-013 | Not Started | -
NF-P4-015 | Week 4 | Submission | Submit on Hack2skill Portal | Fill submission form. Attach pitch deck PDF, video link, GitHub link, deployment link. | All | P0 | 1 | 2026-10-18 | 2026-10-18 | NF-P4-014 | Not Started | Submit TOGETHER, verify each field
NF-P4-016 | Week 4 | Submission | Post-Submission Verification | Verify submission received. Screenshots. Backup all artifacts to Google Drive. | All | P0 | 1 | 2026-10-18 | 2026-10-18 | NF-P4-015 | Not Started | -
NF-P4-017 | Week 4 | Docs | API Contract Documentation Finalization | docs/api-contract.md fully up-to-date. All endpoints, request/response schemas, auth requirements. | Devam | P1 | 2 | 2026-10-15 | 2026-10-16 | NF-P4-001 | Not Started | -
NF-P4-018 | Week 4 | Submission | Team Photos + Bios for Deck | Collect team photos (professional). Write 2-sentence bio each. Add to pitch deck team slide. | Aditya | P1 | 2 | 2026-10-15 | 2026-10-16 | NF-P4-008 | Not Started | -
NF-P4-019 | Week 4 | Demo | Rehearse Full Demo Live | All 3 do a live demo run-through with the deployed app. Fix any UX issues before recording. | All | P0 | 2 | 2026-10-14 | 2026-10-15 | NF-P4-005,NF-P3-020,NF-P3-021 | Not Started | Before recording video
NF-P4-020 | Week 4 | Docs | Data Model Documentation Finalization | docs/data-model.md reviewed and updated. All Firestore collections, sample docs, security rules. | Pranjal | P1 | 2 | 2026-10-15 | 2026-10-16 | NF-P4-001 | Not Started | -

## 3. Phase 0 - Setup
Phase 0 — Pre-Build Setup (Sep 21)
Every task here must be complete before any real code is written. Do NOT skip.
A. GitHub Setup
# | Checklist Item | Owner | Status | Notes
1 | Create org 'google-ai-builder-cup' on GitHub | Aditya | Done
2 | Invite Devam + Pranjal as Owners | Aditya | Done
3 | Accept invitations | Devam + Pranjal | Done
4 | Create NomadFinance repo in the org | Aditya | Done
5 | Change visibility to PUBLIC (Danger Zone) | Aditya | Not Started
6 | Add .gitignore (Python, Node, IDE, .claude/, .env) | Devam | Not Started
7 | Add MIT LICENSE | Aditya | Done
8 | Make org membership public for all 3 | All | Done
9 | Pin repo on each member's profile | All | Done
B. Google Cloud Setup
# | Checklist Item | Owner | Status | Notes
1 | Create GCP project 'nomadfinance-prod' | Devam | Not Started
2 | Enable billing (won't be charged; free tier) | Devam | Not Started
3 | Enable Firestore API | Devam | Not Started
4 | Enable Cloud Run API | Devam | Not Started
5 | Enable Cloud Build API | Devam | Not Started
6 | Enable Cloud Scheduler API | Devam | Not Started
7 | Enable Secret Manager API | Devam | Not Started
8 | Enable Artifact Registry API | Devam | Not Started
9 | Add Pranjal + Aditya as Project Owners (IAM) | Devam | Not Started
C. Firebase Setup
# | Checklist Item | Owner | Status | Notes
1 | Link Firebase to GCP project | Pranjal | Not Started
2 | Enable Authentication (Google + Phone) | Pranjal | Not Started
3 | Initialize Firestore (Native Mode, asia-south1) | Pranjal | Not Started
4 | Enable Cloud Storage bucket | Pranjal | Not Started
5 | Enable Firebase Hosting | Pranjal | Not Started
6 | Enable App Check (reCAPTCHA v3) | Pranjal | Not Started
7 | Enable Cloud Messaging (FCM) | Pranjal | Not Started
8 | Add teammates as Editors on Firebase Console | Pranjal | Not Started
D. Gemini / AI Setup
# | Checklist Item | Owner | Status | Notes
1 | Generate API key from AI Studio (aistudio.google.com/apikey) | Devam | Not Started
2 | Store in GCP Secret Manager (name: gemini-api-key) | Devam | Not Started
3 | Test key with a simple curl to verify quotas | Devam | Not Started
E. Local Environment Setup (Each Teammate)
# | Checklist Item | Owner | Status | Notes
1 | Install Python 3.11 | All | Not Started
2 | Install Node.js 20+ and pnpm | All | Not Started
3 | Install Docker Desktop | All | Not Started
4 | Install Firebase CLI (npm i -g firebase-tools) | All | Not Started
5 | Install gcloud CLI | All | Not Started
6 | Run gcloud auth login + firebase login | All | Not Started
7 | Clone repo locally | All | Not Started
8 | Configure git identity (name + email) | All | Not Started
F. Initial Folder Structure (Sequential Commits — Rotating Ownership)
# | Checklist Item | Owner | Status | Notes
1 | Devam: create backend/ folder + backend/README.md, push | Devam | Not Started
2 | Aditya: pull, create frontend/ + README, commit + push | Aditya | Not Started
3 | Pranjal: pull, create data-scripts/ + README, commit + push | Pranjal | Not Started
4 | Devam: pull, create docs/ + README + design doc, commit + push | Devam | Not Started
5 | Aditya: pull, add .github/pull_request_template.md, push | Aditya | Not Started
G. Communication + Project Management
# | Checklist Item | Owner | Status | Notes
1 | Create team WhatsApp group | Aditya | Not Started
2 | Set up shared Google Drive for pitch assets | Aditya | Not Started
3 | Agree on daily standup time (recommended: 9:30 PM IST) | All | Not Started
4 | Set up GitHub Projects board with columns | Pranjal | Not Started
5 | Add Design Doc + all Mermaid diagrams to repo /docs | Devam | Not Started
H. First Kickoff Call (60 min)
# | Checklist Item | Owner | Status | Notes
1 | Walk through Design Doc together | All | Not Started
2 | Confirm roles per Sheet 1 | All | Not Started
3 | Review Week 1 task board | All | Not Started
4 | Agree on Definition of Done (Sheet 8) | All | Not Started
5 | Agree on Git standards (Sheet 6) | All | Not Started
6 | Agree on AI Assistant Policy (Sheet 12) | All | Not Started

## 4. Sprint Timeline
Sprint Timeline — 4 Weeks
Week-by-week Gantt view. Colored cells indicate assigned days.
Track | Task Group | Phase 0 | Week 1 | [5 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4
|  | Sep 21 | Sep 22 | Sep 23 | Sep 24 | Sep 25 | Sep 26 | Sep 27 | Sep 28 | Sep 29 | Sep 30 | Oct 1 | Oct 2 | Oct 3 | Oct 4 | Oct 5 | Oct 6 | Oct 7 | Oct 8 | Oct 9 | Oct 10 | Oct 11 | Oct 12 | Oct 13 | Oct 14 | Oct 15 | Oct 16 | Oct 17 | Oct 18
Devam | Phase 0: GCP + Gemini + .gitignore | bar: Phase 0 Sep 21
Devam | Backend: FastAPI + Docker Bootstrap | bar: Week 1 Sep 22 to Week 1 Sep 23
Devam | Data: Firestore Security Rules | bar: Week 1 Sep 22 to Week 1 Sep 23
Devam | Frontend: Firebase Auth Integration | bar: Week 1 Sep 23 to Week 1 Sep 24
Devam | Backend: Gemini Client Wrapper | bar: Week 1 Sep 24 to Week 1 Sep 25
Devam | Data: ILO Curation (SG+AE) | bar: Week 1 Sep 22 to Week 1 Sep 26
Devam | Backend: Document Extraction Endpoint | bar: Week 1 Sep 26 to Week 1 Sep 27
Devam | DevOps: FX Refresh Cron | bar: Week 1 Sep 25 to Week 1 Sep 27
Devam | Backend: Contract Shield Extract + Clause Compare | bar: Week 2 Sep 28 to Week 2 Sep 30
Devam | Frontend: Processing Animation | bar: Week 2 Sep 29 to Week 2 Sep 30
Devam | Backend: Contract Shield Cache + Trends Endpoint | bar: Week 2 Sep 30 to Week 2 Oct 3
Devam | Frontend: Corridor Selector UI | bar: Week 2 Oct 4
Devam | Frontend: Radar Report Form | bar: Week 3 Oct 5 to Week 3 Oct 6
Devam | Backend: FIB Bill OCR + Weekly Recompute | bar: Week 3 Oct 6 to Week 3 Oct 9
Devam | Backend: Radar Alert Cron | bar: Week 3 Oct 8 to Week 3 Oct 9
Devam | Frontend: FIB Log Activity UI | bar: Week 3 Oct 10 to Week 3 Oct 11
Devam | E2E Testing + Perf Profiling + Video Upload | bar: Week 4 Oct 12 to Week 4 Oct 15
Devam | Root README + Freeze Branch | bar: Week 4 Oct 15 to Week 4 Oct 17
Aditya | Phase 0: Repo Public + Comms + Docs | bar: Phase 0 Sep 21
Aditya | Frontend: React + Vite Bootstrap | bar: Week 1 Sep 22 to Week 1 Sep 23
Aditya | Frontend: Firebase Hosting Deploy | bar: Week 1 Sep 22 to Week 1 Sep 23
Aditya | Data: ILO Curation (KR+MY) | bar: Week 1 Sep 22 to Week 1 Sep 26
Aditya | Data: Load Corridors to Firestore | bar: Week 1 Sep 24 to Week 1 Sep 25
Aditya | Backend: Firebase Admin + Auth Middleware | bar: Week 1 Sep 25 to Week 1 Sep 26
Aditya | Frontend: i18n + PWA Setup | bar: Week 1 Sep 25 to Week 1 Sep 27
Aditya | Backend: Contract Shield RAG + Translation | bar: Week 2 Sep 29 to Week 2 Oct 1
Aditya | Frontend: Upload UI + Report Card | bar: Week 2 Sep 28 to Week 2 Oct 2
Aditya | Backend: Remittance Transfer Logging | bar: Week 2 Oct 2 to Week 2 Oct 3
Aditya | Frontend: Complaint Download + Comparison Table | bar: Week 2 Oct 3 to Week 3 Oct 5
Aditya | Backend: Radar Embedding + FIB Endpoints | bar: Week 3 Oct 5 to Week 3 Oct 7
Aditya | Frontend: Radar Heatmap Map View | bar: Week 3 Oct 6 to Week 3 Oct 8
Aditya | Frontend: Radar Alerts + FIB Dashboard | bar: Week 3 Oct 9 to Week 3 Oct 11
Aditya | Backend: FIB PDF Export | bar: Week 3 Oct 9 to Week 3 Oct 10
Aditya | Cross-Browser Testing + Deploy Verification | bar: Week 4 Oct 12 to Week 4 Oct 17
Aditya | Demo Video + Deck Visuals | bar: Week 4 Oct 14 to Week 4 Oct 16
Pranjal | Phase 0: Firebase + Project Board | bar: Phase 0 Sep 21
Pranjal | Data: Firestore Schema Design | bar: Week 1 Sep 22
Pranjal | DevOps: Cloud Run Hello World Deploy | bar: Week 1 Sep 23
Pranjal | Data: World Bank Ingestion | bar: Week 1 Sep 23 to Week 1 Sep 24
Pranjal | Frontend: App Shell + Navigation | bar: Week 1 Sep 24 to Week 1 Sep 25
Pranjal | Data: ILO Curation (JP+HK) + Load | bar: Week 1 Sep 22 to Week 1 Sep 27
Pranjal | DevOps: GitHub Actions CI/CD | bar: Week 1 Sep 24 to Week 1 Sep 27
Pranjal | Backend: Contract Shield Detection + Complaint Gen | bar: Week 2 Sep 28 to Week 2 Oct 2
Pranjal | Backend: Remittance Comparison + Recommendation | bar: Week 2 Sep 28 to Week 2 Oct 2
Pranjal | Frontend: Contract Language Switcher | bar: Week 2 Oct 2 to Week 2 Oct 3
Pranjal | Frontend: Remittance Trend Chart | bar: Week 3 Oct 5
Pranjal | Backend: Radar Submission + Aggregation | bar: Week 3 Oct 5 to Week 3 Oct 8
Pranjal | Backend: FIB Categorization | bar: Week 3 Oct 7
Pranjal | Data: Radar + FIB Demo Seed | bar: Week 3 Oct 9 to Week 3 Oct 11
Pranjal | Frontend: Entity Profile + FIB Export UI | bar: Week 3 Oct 8 to Week 3 Oct 11
Pranjal | Security Audit + Submission Brief + Export Deck | bar: Week 4 Oct 13 to Week 4 Oct 16
All | Demo Script + Pitch Deck Content (Together) | bar: Week 4 Oct 14 to Week 4 Oct 16
All | SUBMIT + Post-Submission Verify | bar: Week 4 Oct 18
Legend
Devam | Full-Stack — rotates across backend, frontend, data every week
Aditya | Full-Stack — rotates across backend, frontend, data every week
Pranjal | Full-Stack — rotates across backend, frontend, data every week
All | Shared work — done together (kickoff, testing, deck, submit)

## 5. Workload Balance
Workload Distribution
Estimated hours per teammate per phase. Live formulas — updates as tasks are edited on Sheet 2.
Teammate | Phase 0 | Week 1 | Week 2 | Week 3 | Week 4 | Total
Devam | 3.8 | 48 | 26.3 | 29 | 18.5 | 125.6
Aditya | 3.2 | 32 | 29.3 | 32 | 28 | 124.5
Pranjal | 3.5 | 37 | 30.3 | 39 | 15.5 | 125.3
Team Total | 10.5 | 117 | 85.9 | 100 | 62 | 375.4
Task Count per Teammate
Teammate | Phase 0 | Week 1 | Week 2 | Week 3 | Week 4 | Total
Devam | 4 | 11 | 7 | 7 | 5 | 34
Aditya | 3 | 8 | 7 | 7 | 5 | 30
Pranjal | 2 | 9 | 8 | 11 | 4 | 34
Balance Notes
• NO ROLE SEGREGATION — every teammate touches backend, frontend, and data across every phase.
• Aim for total hours per teammate within ~10% of each other across the sprint.
• If one teammate is falling behind, reassign lower-priority tasks to whoever has capacity.
• 'All' tasks (kickoff, ILO curation, testing, deck, submit) are split equally 3-way.
• ILO curation (12 hrs) is split: Devam=SG+AE, Aditya=KR+MY, Pranjal=JP+HK (4 hrs each).
• Each week: everyone owns at least one backend task + one frontend task + one data task.
• Standups (~15 min/day × 28 days = 7 hrs) not tracked here — considered overhead.
• If mismatch grows during sprint, swap tasks live — the ID stays, the owner changes.
Rebalance (post-review)
• 5 new tasks added: P2-022 (savings calc), P2-023 (report card polish), P3-023 (radar→contract UI), P3-024 (contract→FIB), P3-025 (App Check).
• NF-P3-017 reassigned Aditya → Pranjal to cut Week 3 imbalance (was 37h vs 29h).
• NF-P1-017 hours bumped 12 → 18 for realistic ILO curation (6h × 3 people).
• Post-fix totals: Devam 125.6, Aditya 124.5, Pranjal 125.3 — under 1% spread.

## 6. Git Standards
Git & Version Control Standards
Enterprise-grade Git practices for a 3-person team building a public submission.
Branching Model — GitHub Flow (Lightweight)
Item | Detail
main | Protected. Always deployable. Only merged via reviewed PR from feature branches.
feature/<scope>-<short-desc> | New features. E.g., feature/contract-shield-vision, feature/radar-heatmap
fix/<scope>-<short-desc> | Bug fixes. E.g., fix/auth-token-expiry
chore/<scope>-<short-desc> | Maintenance, deps, tooling. E.g., chore/upgrade-fastapi
docs/<scope> | Documentation only. E.g., docs/architecture-diagram
hotfix/<critical-issue> | Urgent fixes to production. E.g., hotfix/prod-500-on-analyze
Commit Message Convention — Conventional Commits
Item | Detail
Format | <type>(<scope>): <short description in imperative>
Types | feat, fix, chore, docs, refactor, test, perf, style, ci, build
Scope Examples | backend, frontend, data, contract, radar, remittance, fib, ci, docs
Good Examples | feat(contract): add clause-by-clause comparison endpoint ¦ fix(auth): handle expired token gracefully ¦ chore(deps): upgrade pydantic to v2.6
Bad Examples | ❌ 'update code' ¦ ❌ 'fixed bug' ¦ ❌ 'wip' ¦ ❌ 'asked claude to add feature'
Body (Optional) | Blank line, then rationale + what/why. Wrap at 72 chars.
Footer (Optional) | Refs: NF-P2-004 (reference task IDs). Never include: Co-Authored-By, AI attribution.
Length | Subject line ≤ 72 chars. No period at end.
Pull Request Process
Item | Detail
1. Branch | Create feature branch from latest main
2. Small PRs | Target < 400 lines diff. Split large work into multiple PRs.
3. Local Verify | Run linter, type check, and basic tests before pushing
4. Push + PR | Open PR with template. Link task ID (NF-P2-004). Add screenshots for UI changes.
5. Review Required | At least 1 approval from a different teammate before merge
6. CI Checks | All GitHub Actions checks must pass (lint, build, tests)
7. Squash Merge | Use 'Squash and Merge' — keeps main linear. PR title becomes commit message.
8. Delete Branch | Delete the feature branch after merge
PR Template (add to .github/pull_request_template.md)
Item | Detail
Title | <type>(<scope>): <description> — same as commit format
Task ID | Refs: NF-P2-004
What Changed | Bullet list of changes (behavior, not code)
Screenshots | Before/after for UI changes
Testing | How reviewer can verify. Manual steps or automated tests.
Checklist | ☐ Linter passes ☐ Tests pass ☐ Docs updated ☐ No secrets committed ☐ Task ID linked
Code Review Checklist
Item | Detail
Correctness | Does the code do what the PR description says?
Tests | Are new endpoints/features covered by manual verification steps?
Security | No secrets in code? Auth checks in place? Input validation?
Firestore | Are queries indexed? Reads/writes justified? Security rules updated if needed?
Gemini | Correct model tier used? Structured output? Retry logic?
Performance | Any N+1 queries? Big blocking operations?
Naming | Clear variable/function names? Consistent with existing code?
Docs | README, API contract, or docs/ updated where behavior changed?
Style | Passes ruff/black (Python) or ESLint/Prettier (TS)?
No AI Artifacts | No 'Claude:', 'Assistant:', tool call blocks, or AI attribution lines in code/comments
Branch Protection Rules (for main)
Item | Detail
Require PR | Cannot push directly to main. Must go through PR.
Require Reviews | 1 approving review required before merge
Require Status Checks | All CI must pass: lint, build, tests
Require Up-to-date | Branch must be up-to-date with main before merge
Require Linear History | Enforced via squash merge
Include Administrators | Yes — even admins go through PR process (post Week 1)
Note | For POC speed, protection can be minimal in Week 1 while foundation is being laid. Add strict rules from Week 2 onward.
Merge Conflict Protocol
Item | Detail
Prevent | Pull latest main daily. Don't let feature branches drift more than 24hrs.
Resolve | Rebase feature branch onto latest main (`git pull --rebase origin main`) before opening PR.
Conflict | Resolve locally, test, re-push. Never use 'accept theirs' blindly.
Ownership | Author of the PR resolves the conflict, not the reviewer.
Secrets Management
Item | Detail
NEVER commit | .env, service-account.json, API keys, private keys, DB credentials
Local dev | Use .env.local file (gitignored). Provide .env.example as template.
Production | GCP Secret Manager. Mount into Cloud Run as env vars.
Detection | Enable GitHub Secret Scanning (Settings → Code security → Secret scanning)
If exposed | Immediately rotate the key. Revoke from source. Remove from git history via BFG.

## 7. Coding Standards
Coding Standards
Enforce via linters + CI. Everyone runs same tools locally.
Python (Backend) — Style
Formatter | black (line length 100)
Linter | ruff (replaces flake8, isort, pyupgrade)
Type Checker | mypy in --strict mode for services/ folder
Import Order | 1. stdlib 2. third-party 3. local — separated by blank lines (isort handled by ruff)
Naming | snake_case for functions/vars, PascalCase for classes, UPPER_SNAKE for constants
Docstrings | Google-style docstrings for public functions/classes. Skip for trivial helpers.
Type Hints | Required for all function signatures. Use `from __future__ import annotations`.
Async | Prefer async for I/O. Sync for CPU-bound. Never mix without care.
Error Handling | Raise specific exceptions. Never bare except. Log with context.
Python — Structure
Layout | backend/{main.py, routes/, services/, models/, repositories/, utils/}
routes/ | FastAPI router files. Thin — delegate to services.
services/ | Business logic. Testable in isolation.
models/ | Pydantic models for API contracts + Firestore schemas.
repositories/ | Firestore access layer. Encapsulate queries.
Dependencies | requirements.txt pinned. Use uv or pip-tools for lockfile.
Python — Testing
Framework | pytest + pytest-asyncio
Coverage Target | 80% for services/ (business logic). UI-adjacent code exempted.
Fixtures | Use Firebase Emulator for Firestore/Auth in tests.
Mocking | Mock Gemini calls in unit tests. Use real Gemini in integration tests only.
TypeScript (Frontend) — Style
Formatter | Prettier (default config)
Linter | ESLint with @typescript-eslint + eslint-plugin-react-hooks
Strict Mode | tsconfig strict: true. No implicit any.
Naming | camelCase for vars/functions, PascalCase for components/types, UPPER_SNAKE for constants
Component Style | Function components with hooks. No class components.
Props | Define with `interface` for public, `type` for local unions.
Exports | Named exports preferred. Default only for React components.
TypeScript — Structure
Layout | frontend/src/{pages/, components/, hooks/, services/, lib/, types/, i18n/}
pages/ | Route components. Thin.
components/ | Reusable UI. Feature-scoped subfolders (contract/, radar/, remittance/, fib/).
hooks/ | Custom hooks (useAuth, useContract, useCorridor).
services/ | API client wrappers (contractService.ts).
lib/ | Firebase clients, i18n config, utilities.
types/ | Shared TypeScript types matching backend Pydantic models.
TypeScript — Testing
Framework | Vitest for unit + React Testing Library for components
E2E | Playwright for critical user flows in Week 4
Focus | Test business logic hooks + service functions. Skip trivial component snapshots.
Cross-Cutting Standards
Env Vars | Access via config module. Fail fast if missing at startup.
Logging | Structured JSON logs. Include request ID, user ID (hashed), timing.
Errors | Never expose stack traces to users. Return generic errors + log details.
API Versioning | Prefix all endpoints with /api/v1/
Data Validation | Validate at the boundary — Pydantic on ingress, TypeScript types on frontend
File Size | Max ~300 lines per file. Split if larger.
Comments | Explain WHY not WHAT. Skip obvious code.
TODOs | Format: `# TODO(username): description NF-XXX`. Never merge without owner.
Enforcement — CI Pipeline
On PR | Run: ruff check, black --check, mypy, pytest, npm run lint, npm run build
Fail Fast | Any check fail blocks merge until fixed.
Local Pre-commit | Set up husky (frontend) + pre-commit hooks (backend). Same checks as CI.

## 8. Definition of Done
Definition of Done
A task is only 'Done' when all criteria for its type are met. Enforced by reviewer.
Backend Endpoint
☐ | Endpoint defined in FastAPI with Pydantic request/response models
☐ | Firebase Auth token verification (except for public endpoints, which must be marked clearly)
☐ | Structured logging with request ID, user ID (hashed), timing
☐ | Error handling with specific HTTP status codes (4xx for client, 5xx for server)
☐ | Manual test via Swagger /docs successful
☐ | OpenAPI docs updated (auto-generated but sanity check)
☐ | docs/api-contract.md updated
☐ | Rate limiting applied via slowapi if user-facing
Frontend Feature
☐ | Component built with Tailwind + shadcn/ui
☐ | Fully mobile responsive (tested on Chrome DevTools mobile emulator)
☐ | Works on slow network (throttled 3G in DevTools)
☐ | Loading states (skeleton or spinner) visible during async ops
☐ | Error states (network fail, empty data) handled gracefully
☐ | i18n keys added for all user-facing strings (all 6 languages)
☐ | Screenshots added to PR
☐ | Accessibility: keyboard navigable, semantic HTML, aria-labels where needed
Gemini Pipeline Step
☐ | Correct model tier used (2.5 Flash for reasoning, 1.5 Flash for extraction, Flash-Lite for classification/translation)
☐ | Structured output via Pydantic responseSchema — no free-form parsing
☐ | Retry logic via tenacity for transient failures
☐ | Timeout set (default 30s)
☐ | Token usage logged for cost tracking
☐ | Prompt stored in code (not inline) — versioned
☐ | Tested with 3+ diverse inputs (edge cases: long doc, non-English, malformed)
Firestore Schema Change
☐ | Migration script written (or data updated in place if safe)
☐ | Security rules updated to reflect new fields/collections
☐ | docs/data-model.md updated
☐ | Firestore Emulator tests pass
☐ | Version metadata bumped if cached data depends on this
Data Ingestion Script
☐ | Script is idempotent (safe to re-run)
☐ | Validates input data before writing (schema check)
☐ | Logs count of records processed + errors
☐ | Uses service account or admin SDK correctly
☐ | Documented in data-scripts/README.md
Documentation
☐ | Written in Markdown
☐ | Uses consistent formatting (headings, lists, code blocks)
☐ | Reviewed by at least one other teammate
☐ | Committed to /docs folder or updated at file source
☐ | No AI attribution / no ChatGPT-style openers
Bug Fix
☐ | Root cause identified (not just symptom)
☐ | Fix committed with fix() commit type
☐ | Regression test added if fix is non-trivial
☐ | Referenced in commit: 'Fixes NF-XXX'

## 9. Risk Register
Risk Register
Live document. Review weekly. Add new risks as they emerge.
Risk ID | Category | Description | Likelihood | Impact | Mitigation | Owner
R-001 | Technical | Gemini API free tier quota hit during evaluation | Low | High | Tiered model usage (3 models = 3,500 RPD combined). Aggressive Firestore caching. Rate limit per user. | Devam
R-002 | Technical | Cloud Run cold starts cause timeout during judge demo | Medium | Medium | Min instances = 1 during eval week. Pre-warm before demo. Add loading UI to mask latency. | Devam
R-003 | Data | World Bank data quality issues for some corridors | Medium | Low | Manual verification during Week 1 load. Pick 6 well-covered corridors. Document limitations. | Pranjal
R-004 | Data | ILO NATLEX curation takes longer than 12 hours | High | Medium | Start Day 1 of Week 1. Break into sub-tasks per country. Devam/Aditya pair if behind. | Pranjal
R-005 | Team | Teammate falls sick during critical week | Medium | High | Cross-training in Week 1. Pair programming when possible. Task ownership documented. | All
R-006 | Team | Communication breakdown between teammates | Low | High | Mandatory daily standup. Weekly retro. WhatsApp for async. Google Meet for sync. | All
R-007 | Timeline | Contract Shield pipeline more complex than estimated | High | High | Start pipeline foundation Day 1 Week 2. Devam only does backend Week 2. No scope additions. | Devam
R-008 | Timeline | Frontend UI takes longer with 4 pillars | High | High | shadcn/ui speeds this up. Templates reused across pillars. Pranjal helps with data-viz. | Aditya
R-009 | Timeline | Testing week collapses under scope | Medium | High | Test incrementally throughout Weeks 1-3. Reserve full Week 4 for bug fixes + demo. | All
R-010 | External | Frankfurter API downtime during evaluation | Low | Medium | ExchangeRate-API automatic fallback. Firestore cache serves last known rates. | Pranjal
R-011 | External | Firebase / GCP outage during evaluation | Very Low | Very High | Nothing we can do. Judges use same platform they built. Not counted against us. | N/A
R-012 | Cost | Accidentally exceed free tier and get billed | Low | Medium | Set GCP billing budget alerts at $1, $5, $20. Monitor daily. | Devam
R-013 | Security | Accidentally commit API key or secret | Medium | High | GitHub Secret Scanning enabled. .gitignore comprehensive. Pre-commit hooks. Immediate rotation if leaked. | All
R-014 | Demo | Demo video exceeds 4 minutes | Medium | Medium | Script tightly. Rehearse with timer. Multiple takes. Cut aggressively. | Aditya
R-015 | Demo | Live demo link breaks during evaluation | Medium | Very High | Freeze main from Oct 17. No deploys after Oct 17. Backup video shows working state. | Pranjal
R-016 | Process | AI-generated code accidentally committed with attribution | Medium | High | See Sheet 12 AI Assistant Policy. Manual review before commit. .gitignore .claude folder. | All
R-017 | Scope | Adding features mid-sprint from external suggestions | High | Medium | Freeze scope after kickoff. New ideas go to /future-scope.md, not into POC. | Devam

## 10. Daily Standup
Daily Standup Log
9:30 PM IST daily. 15 min max. Format: Yesterday / Today / Blockers
Date | Owner | Yesterday | Today | Blockers | Notes
2026-09-21 (Mon) | Devam
2026-09-21 (Mon) | Aditya
2026-09-21 (Mon) | Pranjal
2026-09-22 (Tue) | Devam
2026-09-22 (Tue) | Aditya
2026-09-22 (Tue) | Pranjal
2026-09-23 (Wed) | Devam
2026-09-23 (Wed) | Aditya
2026-09-23 (Wed) | Pranjal
2026-09-24 (Thu) | Devam
2026-09-24 (Thu) | Aditya
2026-09-24 (Thu) | Pranjal
2026-09-25 (Fri) | Devam
2026-09-25 (Fri) | Aditya
2026-09-25 (Fri) | Pranjal
2026-09-26 (Sat) | Devam
2026-09-26 (Sat) | Aditya
2026-09-26 (Sat) | Pranjal
2026-09-27 (Sun) | Devam
2026-09-27 (Sun) | Aditya
2026-09-27 (Sun) | Pranjal
2026-09-28 (Mon) | Devam
2026-09-28 (Mon) | Aditya
2026-09-28 (Mon) | Pranjal
2026-09-29 (Tue) | Devam
2026-09-29 (Tue) | Aditya
2026-09-29 (Tue) | Pranjal
2026-09-30 (Wed) | Devam
2026-09-30 (Wed) | Aditya
2026-09-30 (Wed) | Pranjal
2026-10-01 (Thu) | Devam
2026-10-01 (Thu) | Aditya
2026-10-01 (Thu) | Pranjal
2026-10-02 (Fri) | Devam
2026-10-02 (Fri) | Aditya
2026-10-02 (Fri) | Pranjal
2026-10-03 (Sat) | Devam
2026-10-03 (Sat) | Aditya
2026-10-03 (Sat) | Pranjal
2026-10-04 (Sun) | Devam
2026-10-04 (Sun) | Aditya
2026-10-04 (Sun) | Pranjal
2026-10-05 (Mon) | Devam
2026-10-05 (Mon) | Aditya
2026-10-05 (Mon) | Pranjal
2026-10-06 (Tue) | Devam
2026-10-06 (Tue) | Aditya
2026-10-06 (Tue) | Pranjal
2026-10-07 (Wed) | Devam
2026-10-07 (Wed) | Aditya
2026-10-07 (Wed) | Pranjal
2026-10-08 (Thu) | Devam
2026-10-08 (Thu) | Aditya
2026-10-08 (Thu) | Pranjal
2026-10-09 (Fri) | Devam
2026-10-09 (Fri) | Aditya
2026-10-09 (Fri) | Pranjal
2026-10-10 (Sat) | Devam
2026-10-10 (Sat) | Aditya
2026-10-10 (Sat) | Pranjal
2026-10-11 (Sun) | Devam
2026-10-11 (Sun) | Aditya
2026-10-11 (Sun) | Pranjal
2026-10-12 (Mon) | Devam
2026-10-12 (Mon) | Aditya
2026-10-12 (Mon) | Pranjal
2026-10-13 (Tue) | Devam
2026-10-13 (Tue) | Aditya
2026-10-13 (Tue) | Pranjal
2026-10-14 (Wed) | Devam
2026-10-14 (Wed) | Aditya
2026-10-14 (Wed) | Pranjal
2026-10-15 (Thu) | Devam
2026-10-15 (Thu) | Aditya
2026-10-15 (Thu) | Pranjal
2026-10-16 (Fri) | Devam
2026-10-16 (Fri) | Aditya
2026-10-16 (Fri) | Pranjal
2026-10-17 (Sat) | Devam
2026-10-17 (Sat) | Aditya
2026-10-17 (Sat) | Pranjal
2026-10-18 (Sun) | Devam
2026-10-18 (Sun) | Aditya
2026-10-18 (Sun) | Pranjal

## 11. Dependencies
Cross-Team Dependencies
Tasks that block other teammates. Handle these first. Communicate ETAs early.
Blocker Task | Blocker Owner | Blocked Task(s) | Blocked Owner | Required By | Coordination Notes
NF-P1-005 Firebase Admin + Auth verification | Aditya | NF-P1-009 (Auth UI), NF-P2-014 (Remittance backend) | Devam, Pranjal | 2026-09-26 | Auth middleware is needed for any protected endpoint. Aditya ships it Day 5 of Week 1.
NF-P1-013 Firestore Schema | Pranjal | All backend endpoints (NF-P2-*, NF-P3-*) | All | 2026-09-22 | Locked before any endpoint work. Reviewed with team at kickoff.
NF-P1-017 ILO Labor Laws in Firestore (Split 3-way) | All | NF-P2-003 (Labor Law RAG), NF-P2-004 (Contract Comparison) | Aditya, Devam | 2026-09-27 | Each person curates 2 countries. Pranjal loads to Firestore last. Blocks all Contract Shield backend.
NF-P1-016 World Bank Corridors in Firestore | Aditya | NF-P2-014 (Remittance Comparison) | Pranjal | 2026-09-25 | Aditya loads the data; Pranjal builds comparison endpoint. Coordinate schema Day 2 of Week 1.
NF-P1-020 GitHub Actions CI/CD | Pranjal | All merge activity from Week 2 onwards | All | 2026-09-27 | Manual deploys accepted only in Week 1. CI must work by Week 2 start.
NF-P2-014 Remittance Backend Endpoint | Pranjal | NF-P2-019 (Remittance Comparison UI) | Aditya | 2026-09-30 | Aditya mocks response until real endpoint is live. Coordinate the response schema Day 1 Week 2.
NF-P2-006 Complaint Letter Generator | Pranjal | NF-P2-013 (Complaint Download UI) | Aditya | 2026-10-02 | Aditya mocks response initially. Schema locked Week 2 Day 1.
NF-P3-002 Radar Embeddings + Clustering | Aditya | NF-P3-007 (Heatmap UI) | Aditya | 2026-10-07 | Same person on both sides — self-blocker. Ship backend first, then UI.
NF-P3-004 Radar Alert Cron | Devam | NF-P3-009 (Alert Feed UI) | Aditya | 2026-10-09 | Alerts must be firing in Firestore before UI can consume them.
NF-P3-011 Bill OCR Endpoint | Devam | NF-P3-016 (Log Activity UI) | Devam | 2026-10-07 | Same person on both sides — coordinate backend response schema first.
NF-P3-013 FIB Weekly Profile Recompute | Devam | NF-P3-017 (Financial Timeline Dashboard) | Pranjal | 2026-10-09 | P3-017 reassigned to Pranjal (was Aditya). Self-blocker like P3-002/P3-011: Devam ships profile schema early Oct 8 so Pranjal can build dashboard against it.
NF-P4-005 Demo Script | All | NF-P4-006 (Record Demo Video) | Aditya | 2026-10-14 | Video cannot start until script is final and approved by team. All 3 co-write.
NF-P4-008 Pitch Deck | All | NF-P4-009 (Deck Visuals) | Aditya | 2026-10-15 | Aditya adds visuals only after content structure is locked. All 3 co-author content.
NF-P3-003 Entity Risk Aggregation | Pranjal | NF-P3-023 (Radar Warnings on Contract Shield UI) | Pranjal | 2026-10-09 | Cross-pillar flow #4. Pranjal ships aggregation first, then wires badge into ContractReport.
NF-P2-004 Clause Comparison | Devam | NF-P3-024 (Contract → FIB Income Source) | Devam | 2026-10-08 | Cross-pillar flow #5. Self-blocker: Devam ships extraction schema before wiring FIB hook.
NF-P3-001 Radar Submit Endpoint | Pranjal | NF-P3-025 (App Check enforcement) | Pranjal | 2026-10-06 | Self-blocker: Pranjal wires App Check middleware to own endpoint. Do BEFORE demo seed data.
NF-P2-011 Contract Report Card UI | Aditya | NF-P2-023 (Report Card Interactions & Polish) | Pranjal | 2026-10-03 | Pair-programming split. Aditya lands base structure, Pranjal polishes interactions same PR.
NF-P2-015 Remittance Historical Trends | Devam | NF-P2-022 (Historical Savings Calculator) | Devam | 2026-10-02 | Self-blocker: same data source. Ship trends endpoint first, then compute savings from it.

## 12. AI Assistant Policy
AI Assistant Usage Policy
How to use Claude/Copilot/AI tools productively without leaking AI attribution or auto-committing code.
Core Principles
• | We MAY use AI assistants (Claude Code, Copilot, ChatGPT) to accelerate development.
• | We MUST review every line of AI-generated code before committing.
• | We MUST NOT let AI tools auto-commit or auto-push to any branch.
• | The public git history must contain ZERO references to AI/Claude/Anthropic/ChatGPT.
• | Commit messages MUST be authored by the teammate committing (in first person, human voice).
• | PRs and reviews MUST be handled by team members, not AI.
Claude Code — Configuration
• | In Claude Code, disable auto-commit and auto-push in settings.
• | Configure Claude Code to write to a local working directory only, not directly to committed files.
• | Add `.claude/` folder to .gitignore (session data, config, memory files).
• | Add `CLAUDE.md` to .gitignore if any project-level Claude config exists.
• | Never accept AI suggestions to run `git commit` or `git push` — do these manually after review.
Commit Message Rules
• | Write commit messages yourself. Never paste AI-generated messages verbatim.
• | NEVER include: 'Co-Authored-By: Claude', 'Generated by Claude', 'Assisted by AI', 'via ChatGPT', etc.
• | NEVER include: emojis like 🤖, references to '.claude/', 'session_' URLs, or Claude Code session links.
• | If AI helps you understand a problem, credit it in your head, not in the commit.
• | Trailer lines like `Refs: NF-XXX` are fine. AI attribution lines are NOT.
Code Review Rules
• | Review AI-generated code as if it were from an intern: don't trust, verify.
• | Rewrite variable names to match team style.
• | Remove AI-typical patterns: excessive comments, verbose docstrings, over-abstracted helpers.
• | Test the code works before pushing. AI hallucinations are real and dangerous.
• | If code has AI-typical structure (e.g., unnecessary try/except everywhere), refactor.
.gitignore Entries (Add to Repo Root)
• | .env, .env.local, .env.*.local
• | .claude/, .claude-code/, .cursor/, .continue/
• | *.pem, service-account*.json, google-credentials.json
• | node_modules/, __pycache__/, *.pyc, .pytest_cache/, .mypy_cache/, .ruff_cache/
• | .DS_Store, Thumbs.db, .idea/, .vscode/settings.json
• | dist/, build/, .next/, .vite/
• | coverage/, .coverage, htmlcov/
• | *.log, npm-debug.log*, yarn-debug.log*
• | docs/scratch/, *.local.md
What TO Include in Commits
• | Real code you understand and can defend in code review.
• | Human-authored comments explaining WHY, not WHAT.
• | Test files that verify actual behavior.
• | Documentation you've reviewed for accuracy.
What NOT to Include in Commits
• | Any file inside .claude/, .cursor/, .continue/ folders.
• | Any commit message referencing AI tools.
• | Any TODO comment like 'TODO: ask Claude about this'.
• | Any AI-inserted attribution or citation in code files.
• | Generated code you don't understand.
• | Copy-pasted AI output without customization to project context.
Safe Workflow with Claude Code
• | 1. Have Claude generate code in a scratchpad/working directory OR in the repo but staging area only.
• | 2. Review the diff manually (git diff).
• | 3. Edit variable names, comments, and structure to match your style.
• | 4. Verify the code runs and tests pass.
• | 5. Write your OWN commit message.
• | 6. Manually `git add` only the files you want.
• | 7. Manually `git commit -m 'your message'`.
• | 8. Manually `git push` after final review.
• | 9. Open PR manually with human-authored description.
If AI Attribution Slips into a Commit
• | Do NOT amend and force-push if others have pulled the commit.
• | Open a new PR with a `chore:` commit that reverts or corrects the attribution.
• | For pre-merge branches (only you have pushed): `git commit --amend`, edit message, force-push.
• | For merged commits: history rewrite requires team coordination. Prefer forward-fix.

## 13. Submission Checklist
Final Submission Checklist — October 18, 2026
Do NOT submit unless every item is checked. Deadline: 11:59 PM IST.
A. Pitch Deck
✓ | Item | Owner
☐ | Follows prescribed Hack2skill template |  | Devam
☐ | Exported to PDF format |  | Aditya
☐ | Slide 1: Title, team names, competition |  | Devam
☐ | Problem statement clearly articulated |  | Devam
☐ | Solution overview with 4 pillars |  | Devam
☐ | Architecture diagram included |  | Devam
☐ | Tech stack — mentions Firebase, Firestore, Cloud Run, Gemini explicitly |  | Devam
☐ | Impact metrics + SDG alignment |  | Devam
☐ | Roadmap slide showing future scalable pillars |  | Devam
☐ | Team slide with photos + roles |  | Aditya
☐ | Uploaded to submission portal |  | Devam
B. Demo Video
✓ | Item | Owner
☐ | 3-4 minutes total (NOT over 4:00) |  | Aditya
☐ | Shows working prototype end-to-end |  | Aditya
☐ | Voice-over narration (clear + audible) |  | Aditya
☐ | Subtitles included for accessibility |  | Aditya
☐ | Uploaded to YouTube (unlisted) OR Vimeo OR Google Drive |  | Aditya
☐ | Video link tested from a different device + incognito |  | All
☐ | Backup copy stored in team Google Drive |  | Aditya
☐ | Video link added to submission portal |  | Devam
C. Deployed Prototype
✓ | Item | Owner
☐ | Frontend deployed on Firebase Hosting — public URL works |  | Aditya
☐ | Backend deployed on Cloud Run — reachable from frontend |  | Devam
☐ | All 4 pillars functional end-to-end |  | All
☐ | Tested on fresh browser + incognito + mobile |  | Pranjal
☐ | Cloud Run min instances = 1 to avoid cold starts during eval |  | Devam
☐ | Firestore has demo data seeded (radar reports, FIB user) |  | Pranjal
☐ | Login flow works with test credentials |  | Aditya
☐ | Main branch tagged v1.0-submission — no deploys after this |  | Aditya
☐ | Prototype URL added to submission portal |  | Devam
D. GitHub Repository
✓ | Item | Owner
☐ | Repo is PUBLIC (not private) |  | Aditya
☐ | README has architecture diagram + tech stack + setup instructions |  | Devam
☐ | Firebase/Firestore/Cloud Run/Gemini usage explained in README |  | Devam
☐ | All 3 team members visible as contributors |  | All
☐ | MIT LICENSE present |  | Aditya
☐ | No secrets committed (scan with git-secrets or gitleaks) |  | Pranjal
☐ | No AI/Claude attribution in commit history |  | All
☐ | docs/ folder contains architecture, data-model, api-contract |  | Devam
☐ | Design Document + all Mermaid diagrams in docs/ |  | Devam
☐ | Repo URL added to submission portal |  | Devam
E. Brief Description Text
✓ | Item | Owner
☐ | 2-3 paragraphs summarizing what NomadFinance is |  | Devam
☐ | Explicitly mentions Firebase, Firestore, Cloud Run, Gemini and how each is used |  | Devam
☐ | Highlights social impact (280M migrant workers, $41B lost annually) |  | Devam
☐ | SDG alignment stated (SDG 8, 10, 16) |  | Devam
☐ | Copy-pasted into submission portal Brief field |  | Devam
F. Final Verification (Day-of Submission)
✓ | Item | Owner
☐ | Every submission portal field filled correctly |  | Devam
☐ | Every URL tested from unrelated device/browser |  | All
☐ | Screenshots of submission confirmation saved |  | Pranjal
☐ | All artifacts backed up in shared Google Drive |  | Pranjal
☐ | Team celebrates 🎉 (this one is important) |  | All

## 14. Parallel Workflow
Parallel Workflow Execution Plan
Day-by-day plan showing what all 3 teammates work on simultaneously. Green = parallel-safe. Red = sync required.
A. Parallelism Rules
PARALLEL-SAFE | Tasks with NO shared file paths and NO dependency links. Anyone can work on any of these tasks simultaneously without conflict.
COORDINATED | Tasks that touch the same file(s) or same Firestore collection. Only one person edits at a time, or split by clear boundaries (e.g. different functions in the same file).
SEQUENTIAL | Task B has a dependency link to Task A. B cannot start until A is committed to main. Use mocked responses to unblock UI work early.
SYNC POINT | Daily standup at 9:30 PM IST + mid-day WhatsApp check on active PR + weekly Sunday retro. Anyone stuck > 4 hours pings the team.
MOCK-FIRST | When frontend depends on a backend endpoint, backend owner ships the API contract (schema in docs/api-contract.md) first. Frontend mocks against that schema until real endpoint lands.
SHARED FILES DANGER | requirements.txt, package.json, Dockerfile, firebase.json, tsconfig.json, .gitignore — anyone editing these announces in WhatsApp first and does a small dedicated PR.
B. Daily Parallel Work Grid (Sep 21 - Oct 18)
Date | Devam (parallel) | Aditya (parallel) | Pranjal (parallel) | Sync / Handoff Notes
2026-09-21 (Sun) | P0: Setup GCP + Gemini API + .gitignore + docs/ | P0: Make repo public + logo idea + Comms channels | P0: Firebase config + Firestore init + Project Board | KICKOFF CALL 60 min. All folder pushes sequential — Devam → Aditya → Pranjal.
2026-09-22 (Mon) | P1-001: FastAPI /health + P1-014: Firestore rules | P1-007: React+Vite bootstrap + P1-024: Logo/color start | P1-013: Firestore schema + P1-015: WB Excel download | 3 fully parallel tracks — different folders, different services.
2026-09-23 (Tue) | P1-002: Dockerize + P1-017: ILO SG+AE curation start | P1-008: Firebase Hosting deploy + P1-017: ILO KR+MY start | P1-003: Cloud Run hello-world + P1-015: parse WB data | P1-003 (Pranjal) unlocks all backend deploys. Everyone starts ILO in parallel.
2026-09-24 (Wed) | P1-004: Gemini Client + P1-027: CORS/rate limit | P1-016: Load corridors + P1-024: brand assets finish | P1-015: WB parse finish + P1-020: GH Actions start | P1-016 (Aditya) needs P1-015 done — coordinate Excel schema at 12 pm.
2026-09-25 (Thu) | P1-004 finish + P1-019: FX cron + P1-029: prompt lib | P1-005: Firebase Admin + P1-017: ILO KR curation | P1-010: App Shell nav + P1-028: logging middleware | Pranjal on frontend (App Shell) — mocks auth until P1-005 lands.
2026-09-26 (Fri) | P1-006: Doc extraction endpoint + P1-017: SG+AE finish | P1-011: i18n setup + P1-017: KR+MY finish + P1-021: landing start | P1-018: Load labor laws + P1-025: Analytics + P1-017: JP+HK finish | P1-017 (ILO) 3-way merge — Pranjal consolidates into single Firestore load.
2026-09-27 (Sat) | P1-022: Onboarding flow + P1-026: Error boundaries | P1-011 finish + P1-012: PWA + P1-021: landing finish | P1-020: GH Actions finish + P1-023: profile page | WEEK 1 REVIEW at 8 PM. Verify: backend deployed, frontend deployed, Firestore seeded, CI green.
2026-09-28 (Sun) | P2-001: Contract Extract Vision | P2-009: Contract Upload UI | P2-002: Language+Country Detect + P2-014: Remittance engine | Pranjal splits time backend (Detect) and backend (Remittance). Isolated.
2026-09-29 (Mon) | P2-004: Clause Comparison (start) | P2-003: Labor Law RAG + P2-010: Processing anim | P2-002 finish + P2-014: Remittance engine | P2-003 (Aditya) blocks P2-004 (Devam). Aditya ships schema by 3 PM.
2026-09-30 (Tue) | P2-004: Clause Comparison finish + P2-015: Trends endpoint | P2-005: Translation + P2-011: Report Card UI | P2-014 finish + P2-006: Complaint gen start | P2-011 (Aditya) can mock report data until P2-004 ships.
2026-10-01 (Wed) | P2-015 finish + P2-022: Savings calc start | P2-011: Report Card UI (heavy) | P2-006: Complaint gen + P2-016: Remittance recommend | Aditya heavy UI day — Devam/Pranjal do NOT push to same frontend files.
2026-10-02 (Thu) | P2-007: Response caching + P2-022: Savings calc finish | P2-011 finish + P2-017: Transfer logging backend | P2-012: Language Switcher UI + P2-006 finish + P2-023: Report Card polish start | Pranjal on frontend (Lang Switcher). Cross-pillar file boundary at ContractReport.tsx.
2026-10-03 (Fri) | P2-008: E2E test (Devam sample) | P2-013: Complaint download UI + P2-017 finish | P2-021: Contract→Radar signal + P2-020: Trend chart start + P2-023: Report Card polish finish | P2-021 (Pranjal) creates radar_reports docs — coordinate schema with P3 team.
2026-10-04 (Sat) | P2-018: Corridor selector UI + P2-008 (Aditya sample) | P2-019: Comparison Table + P2-008 (Pranjal sample) | P2-020: Trend chart finish + P2-021 finish | WEEK 2 REVIEW at 8 PM. Contract Shield E2E walkthrough — all 3 test 1 sample each.
2026-10-05 (Sun) | P3-006: Radar Report Form UI | P3-002: Radar Embeddings + P3-010: FIB endpoints | P3-001: Radar Submit endpoint | P3-001 (Pranjal) ships first; unblocks P3-002 (Aditya) same day.
2026-10-06 (Mon) | P3-006 finish + P3-011: Bill OCR start | P3-007: Heatmap Map (start) | P3-003: Entity risk aggregation + P3-025: App Check on Radar | P3-007 is Aditya's biggest UI task — 2 full days.
2026-10-07 (Tue) | P3-011 finish + P3-013: FIB Weekly Recompute (start) | P3-007: Heatmap continue | P3-012: FIB Categorization + P3-025: App Check finish | 3 fully parallel tracks — different pillars, no file collisions.
2026-10-08 (Wed) | P3-004: Radar Alert Cron + P3-024: Contract→FIB start | P3-007 finish + P3-014: FIB PDF Export (start) | P3-005: Radar Seed Data + P3-020: Sample contracts | P3-020 (Pranjal) creates demo contract set — required for P4-019 rehearsal.
2026-10-09 (Thu) | P3-013 finish + P3-004 finish + P3-024: Contract→FIB finish | P3-009: Alert Feed UI + P3-014 finish + P3-022: Radar warnings in Remittance | P3-005 finish + P3-008: Entity Profile Page + P3-023: Radar warnings on Contract UI | P3-022 shows cross-pillar story — Aditya coordinates with Pranjal's aggregation data.
2026-10-10 (Fri) | P3-016: FIB Log Activity UI + P3-021: Demo users (start) | P3-019: Home Dashboard (start) | P3-018: Portable Report Export UI + P3-023: Radar warnings finish | Pranjal on frontend (Portable Report). Isolated component.
2026-10-11 (Sat) | P3-016 finish + P3-021 finish | P3-019 finish | P3-018 finish + P3-017: Timeline Dashboard (reassigned) | WEEK 3 REVIEW. All 4 pillars must work end-to-end today. Bug list frozen.
2026-10-12 (Sun) | P4-001: E2E all pillars (Devam suite) | P4-001 + P4-002: Cross-browser testing | P4-001 (Pranjal suite) | Split E2E by pillar: Devam=Contract+FIB, Aditya=Frontend cross-browser, Pranjal=Remittance+Radar+Security.
2026-10-13 (Mon) | P4-003: Perf profiling | P4-002 finish + fix bugs from Day 12 | P4-004: Security audit | Bug-fix day. No new features.
2026-10-14 (Tue) | P4-005: Demo script (co-author) | P4-005 co-author + P4-006: Demo video prep | P4-005 co-author + P4-008: Deck outline start | P4-005 = team writing session. 3-4 pm on Google Meet.
2026-10-15 (Wed) | P4-007: Upload video + P4-011: README (start) | P4-006: Record demo video + P4-009: Deck visuals | P4-008: Deck content + P4-004 fixes | Video + deck day. Devam/Pranjal don't disturb Aditya during recording.
2026-10-16 (Thu) | P4-011 finish + P4-017: API docs | P4-009 finish + P4-010: Export PDF + P4-018: Team bios | P4-012: Submission brief + P4-020: Data model docs | Everything on paper today. Submission portal opens tomorrow.
2026-10-17 (Fri) | P4-014: Freeze main branch (tag v1.0) | P4-013: Final deploy verification | Deploy verify support + backup all artifacts | NO MORE COMMITS after 8 PM. Any bug found = document, don't fix.
2026-10-18 (Sat) | P4-015: Submit portal (co-run) | P4-015 co-run + P4-016 co-run | P4-016: Post-submission verify (co-run) | SUBMISSION DAY. All 3 on Google Meet. Submit BEFORE 6 PM IST to have buffer.
C. Critical Path (Zero Parallelism Possible)
Chain 1: Backend Foundation | NF-P0-004 (GCP project) → NF-P1-001 (FastAPI) → NF-P1-002 (Docker) → NF-P1-003 (Cloud Run deploy) — MUST be sequential; nothing backend runs without this
Chain 2: Frontend Foundation | NF-P0-005 (Firebase) → NF-P1-007 (React) → NF-P1-008 (Hosting deploy) → NF-P1-009 (Auth) — MUST be sequential
Chain 3: Data Foundation | NF-P1-013 (Schema) → NF-P1-014 (Rules) → data ingest tasks → application queries — MUST be sequential
Chain 4: Contract Shield Pipeline | P2-001 Extract → P2-002 Detect → P2-003 RAG → P2-004 Compare → P2-005 Translate → P2-006 Complaint — sequential at pipeline step level; each step needs prior step's output schema
Chain 5: Demo → Video → Submission | P3-020+P3-021 (demo data) → P4-005 (script) → P4-019 (rehearsal) → P4-006 (record) → P4-007 (upload) → P4-015 (submit) — MUST NOT slip; each step waits for prior
D. Handoff Matrix — When A's Task Unblocks B
When | Handoff | From | To | Rule
Sep 23 3 PM | Cloud Run deployed → backend team can push endpoints | Pranjal | Devam+Aditya | Announce in WhatsApp with deployed URL
Sep 24 12 PM | WB parsed schema → corridor load task | Pranjal | Aditya | Post JSON schema in WhatsApp
Sep 26 EOD | ILO curation complete → Firestore load | All 3 | Pranjal | Pranjal merges 3 JSON files into single load script
Sep 27 EOD | Firebase Admin auth ready → any protected endpoint | Aditya | Devam+Pranjal | Post middleware usage example in docs
Sep 29 3 PM | P2-003 Labor Law RAG schema → P2-004 Clause Comparison | Aditya | Devam | Aditya posts API response shape early morning
Sep 30 3 PM | P2-004 Comparison schema → P2-011 Report Card UI | Devam | Aditya | Mock JSON published to /docs/mocks/contract-report.json
Oct 2 EOD | P2-006 Complaint schema → P2-013 Download UI | Pranjal | Aditya | Mock text ready for Aditya to build against
Oct 3 EOD | P2-021 Radar signal schema → future P3 aggregation | Pranjal | Pranjal (P3 self) | Solo handoff — self-document
Oct 5 EOD | P3-001 Radar endpoint → P3-002 embeddings | Pranjal | Aditya | Response schema needed early Oct 5
Oct 7 EOD | P3-003 Aggregation → P3-022 UI warnings | Pranjal | Aditya | Aggregation output feeds heatmap + warning UI
Oct 8 EOD | P3-004 Alert data → P3-009 Alert Feed UI | Devam | Aditya | FCM payload schema documented
Oct 9 EOD | P3-013 Profile Recompute → P3-017 Dashboard UI | Devam | Aditya | Sample profile JSON published
Oct 10 EOD | P3-020 Sample contracts + P3-021 demo users → P4-019 rehearsal | Pranjal+Devam | All 3 | Demo dataset frozen — no changes after
Oct 15 EOD | P4-006 Video final cut → P4-007 Upload | Aditya | Devam | MP4 handed over via Drive; Devam uploads YouTube
Oct 17 8 PM | P4-014 main freeze → NO MORE COMMITS | Devam | All 3 | Tag v1.0. Any post-freeze commit requires 3-person approval.